## Sheet1
Cost Estimate
Project Name: Board Game Development | Date:05/23/2020
Note: Enter your WBS, hours, labor rates, etc. Add/delete rows and columns as needed and check all formulas (bolded below).
| Internal | $/hour | Internal | External | $/hour | External | Total | Non-labor $ | Total Cost
WBS Categories | Labor |  | $ Total | Labor |  | $ Total | Labor
1. Initiating | 150 | 65 | 9750 |  |  | 0 | 9750 |  | 9750
2. Planning | 250 | 60 | 15000 |  |  | 0 | 15000 |  | 15000
3. Executing |  |  | 0 |  |  | 0 | 0 |  | 0
3.1 Course design and development |  |  | 0 |  |  | 0 | 0 |  | 0
3.1.1 Supplier management training | 200 | 60 | 12000 | 300 | 100 | 30000 | 42000 | 6000 | 48000
3.1.2 Negotiating skills training | 100 | 55 | 5500 | 200 | 100 | 20000 | 25500 | 5000 | 30500
3.1.3 Project management training | 200 | 60 | 12000 | 100 | 100 | 10000 | 22000 | 5000 | 27000
3.1.4 Software applications training | 150 | 60 | 9000 | 400 | 100 | 40000 | 49000 | 5000 | 54000
3.2 Course administration | 200 | 55 | 11000 | 300 | 150 | 45000 | 56000 | 4000 | 60000
3.3.Course evaluation | 200 | 55 | 11000 |  |  | 0 | 11000 |  | 11000
3.4 Stakeholder communications | 100 | 55 | 5500 |  |  | 0 | 5500 |  | 5500
4. Monitoring and Controlling | 300 | 55 | 16500 |  |  | 0 | 16500 |  | 16500
5. Closing | 100 | 55 | 5500 |  |  | 0 | 5500 |  | 5500
Subtotal | [8 empty] | 282750
Reserves |  |  | 0 |  |  | 0 | 0 |  | 10300
Total | 1950 |  | 122500 | 1200 | 550 | 145000 | 257750 | 25000 | 293050