## Sheet1 (2)
Issue Log for Board Game Development
Prepared by: Neelesh Saladi Date: June 2, 2020
Issue | Description | Impact | Date Reported | Reported By | Assigned To | Priority | Due Date | Status | Comments
(H/M/L)
1 | The marketing manager assigned to the project left the organization | Delay in promotion of website | May 21st 2020 | Vineetha Yenugula | Revanth Davuluri | H | 2020-05-24 | Closed | A new marketing manager has been appointed.
2 | Documentation format changes | Documentation structure is unsatisfactory | May 22nd 2020 | Bharath kumar Gandhasiri | Tejaswi Reddy Kandula | M | 2020-05-25 | In progress | The documentation changes are under progress
3 | Not enough funding to complete the project | Delay in project completion | May 24th 2020 | Tejaswi Reddy Kandula | Neelesh saladi | H | 2020-05-28 | Open | Got approval from sponsor.
4 | Need more developers | Cannot proceed further with ontime schedule | May 25th 2020 | Neelesh Saladi | Bharath Kumar Gandhasiri | M | 2020-05-27 | Closed | Recruiting.
5 | Absence of team member | Slower pace of work | June 1 2020 | Bharath Kumar Gandhasiri | Vineetha Yenugula | M | 2020-06-02 | Closed | Project manager has health issues and the sub-project manager took longer to get the jobs done.
6 | Pending to receive the game UI | Delay in product delivery | June 2nd 2020 | Vineetha Yenugula | Revanth Davuluri | M | 2020-06-03 | Open | Test reports were generated.