## Sheet1
Risk Register for Board Game Development - Application
Date: 05/28/2020
Project Name: |  | Board Game Development
ID No. | Rank | Risk | Description | Category | Root Cause | Triggers | Potential Responses | Risk Owner | Probability | Impact | Status
4210 | 1 | Rise in Budget | Estimating the budget is critical but It is important to estimate the budget and go according to the plan. | Financial Risk | Improper estimations | Rise in salaries | Risk Acceptance | Financial Manager | High | High | Prediction
90 | 2 | Applications as similar | If there are applications similar to the produced one.No one shows interest in it.They tend to use the old one as they are used to it.It should be new and interesting.It should grab the attention in the market. | Market Risk | Existing similar applications | Applications | Risk Acceptance | Program manager | High | High | Mitigated
23 | 3 | Time Maintainance | Each day's work should be done as per plan.It is going to burden if there is no proper time management.It effects project which results in client dissatification. | Process Risk | wrong estimation of time | unable to finish the scheduled work on time | Risk Mitigation | Project Manager & Team | Medium | Low | Expected
28 | 4 | Exit of Team member | If all of sudden a team mate resigns,it is difficult to finish the target as planned.Even a new member is appointed he should be trained and udjested according to requirements. | People Risk | lack of enthusiasm | dissatisfied team member | Risk Mitigation | Project Manager | Low | Medium | Expected
89 | 5 | Natural Disasters | Such threats can not be handled. They are unpredictable, so they have an effect on results.There is no avoidance to these type of risks. | Financial Risk, Schedule risk | Not having a disaster recovery methods | Not being prepared | Risk Acceptance | Organization | low | High | Anticipated
4623 | 6 | Scope of project | If the product owner is not happy with the scope he might make change requests.It is hard to maintain scope as many people get involved from start to end | Process Risk | Improper Scope estimations/Improper deliverable | Product owners dissatisfaction | Risk Mitigation | Project Manager | High | Medium | Prediction
345 | 7 | User experience | user may not like graphical user interface | Design Risk | Insufficient user feedack/involvement during software selection/implementation | bad user experience | need to collect customer feedback | Project Manager | Medium | High | open
43 | 8 | Server support | server maynot support for larger number of users | Maintainence Risk | present servers not able to support huge number of users at a time | application hang or slow response | increase server capacity | Team Lead | Medium | Medium | Prediction